## Sheet2 (hidden)
Discipline | (All)
Row Labels | Count of Doc No | Count of Doc No | Column Labels | [5 empty] | Row Labels | Count of Doc No
Approved | 93 | Row Labels | Approved | For Review | Issued for Construction | Pending | Rejected | Grand Total | A | 148
For Review | 101 | Architectural | 2 |  |  |  | 2 | 4 | B | 118
Issued for Construction | 85 | Architecture | 16 | 17 | 17 | 21 | 20 | 91 | C | 131
Pending | 107 | Civil | 23 | 25 | 17 | 17 | 24 | 106 | D | 103
Rejected | 114 | Electrical | 16 | 17 | 16 | 24 | 28 | 101 | Grand Total | 500
Grand Total | 500 | Mechanical | 21 | 16 | 14 | 21 | 20 | 92
|  | Plumbing | 15 | 26 | 21 | 24 | 20 | 106
|  | Grand Total | 93 | 101 | 85 | 107 | 114 | 500
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard
DOCUMENTS PENDING APPROVAL
107
DOCUMENTS OVERDUE
64
ABC PROJECT - DOCUMENT MANAGEMENT DASHBOARD
TOTAL DOCUMENTS
500
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Document_Data
Doc No | Title | Discipline | Revision | Issued Date | Approved Date | Status | Days Overdue
DRG-001 | Drawing 1 | Plumbing | A | 2025-04-13 | 2025-04-22 | Pending | 211 | Total Documents | 500
DRG-002 | Drawing 2 | Plumbing | C | 2025-05-15 | 2025-05-20 | Rejected | 0 | Documents Pending Approval | 107
DRG-003 | Drawing 3 | Electrical | A | 2025-04-21 | 2025-04-26 | Rejected | 0 | Documents Overdue | 64
DRG-004 | Drawing 4 | Mechanical | A | 2025-06-16 |  | Rejected | 0
DRG-005 | Drawing 5 | Architectural | A | 2025-09-13 |  | Rejected | 0
DRG-006 | Drawing 6 | Civil | A | 2025-02-14 | 2025-02-20 | Rejected | 0
DRG-007 | Drawing 7 | Civil | A | 2025-10-13 | 2025-10-22 | Approved | 0
DRG-008 | Drawing 8 | Mechanical | A | 2025-01-14 |  | Rejected | 0
DRG-009 | Drawing 9 | Mechanical | A | 2025-04-06 | 2025-04-14 | Approved | 0
DRG-010 | Drawing 10 | Mechanical | A | 2025-10-17 | 2025-10-25 | Pending | 24
DRG-011 | Drawing 11 | Architectural | D | 2025-03-14 | 2025-03-19 | Approved | 0
DRG-012 | Drawing 12 | Electrical | C | 2025-07-04 | 2025-07-08 | Pending | 129
DRG-013 | Drawing 13 | Mechanical | C | 2025-08-15 | 2025-08-30 | Rejected | 0
DRG-014 | Drawing 14 | Civil | C | 2025-05-17 | 2025-05-28 | Pending | 177
DRG-015 | Drawing 15 | Electrical | C | 2025-09-02 | 2025-09-17 | Pending | 69
DRG-016 | Drawing 16 | Plumbing | A | 2025-05-22 | 2025-05-29 | Approved | 0
DRG-017 | Drawing 17 | Architectural | D | 2025-04-17 | 2025-04-23 | Approved | 0
DRG-018 | Drawing 18 | Electrical | A | 2025-05-13 | 2025-05-22 | Approved | 0
DRG-019 | Drawing 19 | Mechanical | D | 2025-06-21 | 2025-06-28 | Approved | 0
DRG-020 | Drawing 20 | Electrical | C | 2025-03-27 | 2025-04-09 | Approved | 0
DRG-021 | Drawing 21 | Architectural | A | 2025-07-07 |  | Rejected | 0
DRG-022 | Drawing 22 | Electrical | C | 2025-04-28 |  | Rejected | 0
DRG-023 | Drawing 23 | Civil | B | 2025-04-17 | 2025-04-24 | Pending | 207
DRG-024 | Drawing 24 | Civil | A | 2025-06-04 | 2025-06-15 | Pending | 159
DRG-025 | Drawing 25 | Plumbing | A | 2025-05-26 |  | Pending | 168
DRG-026 | Drawing 26 | Plumbing | C | 2025-09-30 |  | Pending | 41
DRG-027 | Drawing 27 | Plumbing | B | 2025-10-20 | 2025-11-02 | Pending | 21
DRG-028 | Drawing 28 | Plumbing | B | 2025-05-08 | 2025-05-17 | Rejected | 0
DRG-029 | Drawing 29 | Plumbing | A | 2025-06-06 | 2025-06-13 | Rejected | 0
DRG-030 | Drawing 30 | Plumbing | D | 2025-09-08 | 2025-09-13 | Rejected | 0
DRG-031 | Drawing 31 | Mechanical | B | 2025-01-24 |  | Rejected | 0
DRG-032 | Drawing 32 | Electrical | A | 2025-09-19 | 2025-09-21 | Rejected | 0
DRG-033 | Drawing 33 | Electrical | D | 2025-03-16 | 2025-03-23 | Pending | 239
DRG-034 | Drawing 34 | Plumbing | C | 2025-08-04 | 2025-08-10 | Rejected | 0
DRG-035 | Drawing 35 | Electrical | D | 2025-06-03 | 2025-06-05 | Approved | 0
DRG-036 | Drawing 36 | Civil | B | 2025-09-03 | 2025-09-04 | Rejected | 0
DRG-037 | Drawing 37 | Civil | D | 2025-08-02 | 2025-08-10 | Pending | 100
DRG-038 | Drawing 38 | Plumbing | A | 2025-03-14 | 2025-03-27 | Pending | 241
DRG-039 | Drawing 39 | Mechanical | A | 2025-03-15 |  | Pending | 240
DRG-040 | Drawing 40 | Electrical | B | 2025-07-23 | 2025-08-03 | Rejected | 0
DRG-041 | Drawing 41 | Electrical | A | 2025-06-19 |  | For Review | 0
DRG-042 | Drawing 42 | Mechanical | C | 2025-02-28 | 2025-03-05 | Issued for Construction | 0
DRG-043 | Drawing 43 | Architecture | A | 2025-08-20 | 2025-08-28 | Rejected | 0
DRG-044 | Drawing 44 | Mechanical | C | 2025-07-25 | 2025-08-03 | Approved | 0
DRG-045 | Drawing 45 | Mechanical | B | 2025-03-12 |  | Rejected | 0
DRG-046 | Drawing 46 | Architecture | C | 2025-08-18 |  | Rejected | 0
DRG-047 | Drawing 47 | Electrical | B | 2025-04-25 | 2025-05-04 | Rejected | 0
DRG-048 | Drawing 48 | Mechanical | C | 2025-06-21 | 2025-06-25 | Pending | 141
DRG-049 | Drawing 49 | Architecture | D | 2025-01-03 | 2025-01-13 | Pending | 0
DRG-050 | Drawing 50 | Electrical | A | 2025-05-26 |  | Rejected | 0
DRG-051 | Drawing 51 | Civil | B | 2025-04-15 |  | Approved | 0
DRG-052 | Drawing 52 | Plumbing | A | 2025-03-27 |  | Rejected | 0
DRG-053 | Drawing 53 | Electrical | C | 2025-01-04 | 2025-01-16 | Issued for Construction | 0
DRG-054 | Drawing 54 | Architecture | D | 2025-08-20 | 2025-08-22 | For Review | 0
DRG-055 | Drawing 55 | Plumbing | A | 2025-04-28 | 2025-04-28 | Issued for Construction | 0
DRG-056 | Drawing 56 | Electrical | D | 2025-05-27 |  | For Review | 0
DRG-057 | Drawing 57 | Architecture | A | 2025-03-23 | 2025-03-24 | Pending | 0
DRG-058 | Drawing 58 | Plumbing | A | 2025-01-14 | 2025-01-14 | Issued for Construction | 0
DRG-059 | Drawing 59 | Plumbing | B | 2025-08-07 |  | Approved | 0
DRG-060 | Drawing 60 | Plumbing | B | 2025-10-28 | 2025-11-12 | Pending | 239
DRG-061 | Drawing 61 | Civil | B | 2025-01-28 |  | For Review | 0
DRG-062 | Drawing 62 | Plumbing | C | 2025-01-03 | 2025-01-13 | Approved | 0
DRG-063 | Drawing 63 | Electrical | B | 2025-02-20 | 2025-03-02 | Pending | 124
DRG-064 | Drawing 64 | Architecture | D | 2025-06-03 | 2025-06-09 | Pending | 0
DRG-065 | Drawing 65 | Electrical | C | 2025-05-31 | 2025-06-10 | For Review | 0
DRG-066 | Drawing 66 | Mechanical | A | 2025-07-13 |  | Issued for Construction | 0
DRG-067 | Drawing 67 | Civil | C | 2025-02-23 | 2025-03-09 | Issued for Construction | 0
DRG-068 | Drawing 68 | Mechanical | A | 2025-07-05 | 2025-07-10 | Pending | 238
DRG-069 | Drawing 69 | Electrical | D | 2025-07-03 | 2025-07-18 | For Review | 0
DRG-070 | Drawing 70 | Electrical | A | 2025-02-03 | 2025-02-18 | Pending | 224
DRG-071 | Drawing 71 | Civil | C | 2025-08-11 | 2025-08-13 | Issued for Construction | 0
DRG-072 | Drawing 72 | Civil | C | 2025-08-16 | 2025-08-31 | Rejected | 0
DRG-073 | Drawing 73 | Civil | C | 2025-10-23 | 2025-11-03 | Approved | 0
DRG-074 | Drawing 74 | Plumbing | B | 2025-08-28 | 2025-09-05 | For Review | 0
DRG-075 | Drawing 75 | Civil | D | 2025-01-20 | 2025-01-20 | Rejected | 0
DRG-076 | Drawing 76 | Civil | D | 2025-03-24 |  | For Review | 0
DRG-077 | Drawing 77 | Electrical | C | 2025-01-12 |  | Pending | 200
DRG-078 | Drawing 78 | Mechanical | A | 2025-09-24 | 2025-09-30 | Approved | 0
DRG-079 | Drawing 79 | Electrical | D | 2025-08-20 | 2025-08-28 | Pending | 280
DRG-080 | Drawing 80 | Mechanical | D | 2025-01-29 | 2025-02-09 | Rejected | 0
DRG-081 | Drawing 81 | Architecture | B | 2025-09-25 | 2025-10-02 | For Review | 0
DRG-082 | Drawing 82 | Plumbing | C | 2025-10-20 | 2025-10-20 | For Review | 0
DRG-083 | Drawing 83 | Electrical | B | 2025-07-27 | 2025-08-03 | Rejected | 0
DRG-084 | Drawing 84 | Electrical | A | 2025-09-08 |  | Pending | 138
DRG-085 | Drawing 85 | Electrical | A | 2025-05-28 | 2025-06-03 | Pending | 0
DRG-086 | Drawing 86 | Plumbing | B | 2025-08-29 | 2025-09-04 | For Review | 0
DRG-087 | Drawing 87 | Mechanical | A | 2025-10-11 | 2025-10-15 | For Review | 0
DRG-088 | Drawing 88 | Electrical | B | 2025-10-14 | 2025-10-14 | Approved | 0
DRG-089 | Drawing 89 | Electrical | B | 2025-09-30 | 2025-10-15 | Pending | 0
DRG-090 | Drawing 90 | Civil | A | 2025-04-11 |  | Rejected | 0
DRG-091 | Drawing 91 | Plumbing | A | 2025-03-28 | 2025-04-12 | For Review | 0
DRG-092 | Drawing 92 | Mechanical | A | 2025-06-08 | 2025-06-10 | Pending | 218
DRG-093 | Drawing 93 | Civil | B | 2025-07-14 | 2025-07-19 | Approved | 0
DRG-094 | Drawing 94 | Mechanical | A | 2025-06-02 | 2025-06-15 | Pending | 254
DRG-095 | Drawing 95 | Plumbing | B | 2025-10-06 | 2025-10-11 | Approved | 0
DRG-096 | Drawing 96 | Civil | D | 2025-04-10 | 2025-04-16 | Pending | 0
DRG-097 | Drawing 97 | Plumbing | D | 2025-09-09 | 2025-09-11 | For Review | 0
DRG-098 | Drawing 98 | Electrical | C | 2025-05-03 | 2025-05-05 | Issued for Construction | 0
DRG-099 | Drawing 99 | Mechanical | B | 2025-03-06 | 2025-03-08 | For Review | 0
DRG-100 | Drawing 100 | Civil | D | 2025-10-03 | 2025-10-04 | Rejected | 0
DRG-101 | Drawing 101 | Architecture | B | 2025-07-06 |  | Rejected | 0
DRG-102 | Drawing 102 | Mechanical | A | 2025-06-04 |  | For Review | 0
DRG-103 | Drawing 103 | Plumbing | A | 2025-06-20 | 2025-07-01 | For Review | 0
DRG-104 | Drawing 104 | Architecture | B | 2025-02-20 | 2025-02-21 | For Review | 0
DRG-105 | Drawing 105 | Electrical | A | 2025-02-12 | 2025-02-13 | Rejected | 0
DRG-106 | Drawing 106 | Civil | A | 2025-08-21 | 2025-08-28 | For Review | 0
DRG-107 | Drawing 107 | Plumbing | A | 2025-10-20 | 2025-10-26 | For Review | 0
DRG-108 | Drawing 108 | Plumbing | C | 2025-06-22 |  | Pending | 0
DRG-109 | Drawing 109 | Civil | C | 2025-10-22 | 2025-10-24 | Approved | 0
DRG-110 | Drawing 110 | Civil | B | 2025-05-12 | 2025-05-17 | For Review | 0
DRG-111 | Drawing 111 | Plumbing | A | 2025-04-07 | 2025-04-17 | Rejected | 0
DRG-112 | Drawing 112 | Electrical | A | 2025-06-16 | 2025-06-28 | Rejected | 0
DRG-113 | Drawing 113 | Mechanical | A | 2025-04-24 | 2025-05-09 | For Review | 0
DRG-114 | Drawing 114 | Electrical | C | 2025-05-19 | 2025-06-01 | Rejected | 0
DRG-115 | Drawing 115 | Plumbing | A | 2025-10-13 | 2025-10-21 | Issued for Construction | 0
DRG-116 | Drawing 116 | Electrical | D | 2025-02-27 | 2025-03-12 | Issued for Construction | 0
DRG-117 | Drawing 117 | Architecture | C | 2025-03-29 | 2025-04-11 | Issued for Construction | 0
DRG-118 | Drawing 118 | Electrical | A | 2025-10-22 | 2025-10-23 | Pending | 100
DRG-119 | Drawing 119 | Civil | D | 2025-02-13 | 2025-02-24 | For Review | 0
DRG-120 | Drawing 120 | Plumbing | B | 2025-08-11 | 2025-08-18 | For Review | 0
DRG-121 | Drawing 121 | Architecture | B | 2025-08-07 |  | For Review | 0
DRG-122 | Drawing 122 | Electrical | D | 2025-03-22 | 2025-04-05 | Issued for Construction | 0
DRG-123 | Drawing 123 | Mechanical | C | 2025-02-03 | 2025-02-09 | Approved | 0
DRG-124 | Drawing 124 | Plumbing | B | 2025-04-21 | 2025-04-28 | For Review | 0
DRG-125 | Drawing 125 | Civil | A | 2025-10-18 | 2025-10-19 | Issued for Construction | 0
DRG-126 | Drawing 126 | Mechanical | A | 2025-02-02 |  | Rejected | 0
DRG-127 | Drawing 127 | Mechanical | A | 2025-04-19 | 2025-05-03 | Approved | 0
DRG-128 | Drawing 128 | Mechanical | A | 2025-02-20 | 2025-02-25 | Rejected | 0
DRG-129 | Drawing 129 | Civil | D | 2025-02-09 | 2025-02-21 | Issued for Construction | 0
DRG-130 | Drawing 130 | Architecture | C | 2025-03-27 |  | Approved | 0
DRG-131 | Drawing 131 | Plumbing | A | 2025-06-20 | 2025-06-25 | Rejected | 0
DRG-132 | Drawing 132 | Electrical | D | 2025-07-23 | 2025-07-29 | For Review | 0
DRG-133 | Drawing 133 | Mechanical | C | 2025-03-30 | 2025-04-14 | Approved | 0
DRG-134 | Drawing 134 | Civil | A | 2025-01-31 | 2025-02-04 | Rejected | 0
DRG-135 | Drawing 135 | Civil | B | 2025-03-10 | 2025-03-23 | Rejected | 0
DRG-136 | Drawing 136 | Plumbing | C | 2025-01-04 | 2025-01-11 | Issued for Construction | 0
DRG-137 | Drawing 137 | Mechanical | C | 2025-04-01 | 2025-04-14 | Pending | 0
DRG-138 | Drawing 138 | Civil | D | 2025-05-03 | 2025-05-05 | Rejected | 0
DRG-139 | Drawing 139 | Mechanical | B | 2025-02-20 | 2025-02-21 | Issued for Construction | 0
DRG-140 | Drawing 140 | Mechanical | A | 2025-01-04 | 2025-01-19 | Pending | 80
DRG-141 | Drawing 141 | Mechanical | A | 2025-02-20 |  | For Review | 0
DRG-142 | Drawing 142 | Electrical | A | 2025-05-11 | 2025-05-21 | For Review | 0
DRG-143 | Drawing 143 | Mechanical | A | 2025-05-11 | 2025-05-12 | Pending | 0
DRG-144 | Drawing 144 | Architecture | A | 2025-07-31 | 2025-08-11 | Issued for Construction | 0
DRG-145 | Drawing 145 | Plumbing | B | 2025-04-24 | 2025-04-29 | For Review | 0
DRG-146 | Drawing 146 | Architecture | B | 2025-01-09 | 2025-01-13 | Pending | 0
DRG-147 | Drawing 147 | Electrical | D | 2025-06-21 | 2025-07-04 | Pending | 268
DRG-148 | Drawing 148 | Electrical | B | 2025-03-09 | 2025-03-15 | Issued for Construction | 0
DRG-149 | Drawing 149 | Architecture | B | 2025-05-09 | 2025-05-18 | Rejected | 0
DRG-150 | Drawing 150 | Architecture | A | 2025-06-03 |  | Approved | 0
DRG-151 | Drawing 151 | Mechanical | C | 2025-09-24 | 2025-10-06 | Rejected | 0
DRG-152 | Drawing 152 | Architecture | D | 2025-05-04 | 2025-05-16 | Pending | 0
DRG-153 | Drawing 153 | Civil | D | 2025-07-28 | 2025-07-28 | Issued for Construction | 0
DRG-154 | Drawing 154 | Mechanical | A | 2025-06-11 |  | Approved | 0
DRG-155 | Drawing 155 | Electrical | D | 2025-02-28 | 2025-03-10 | Rejected | 0
DRG-156 | Drawing 156 | Civil | D | 2025-04-13 | 2025-04-18 | For Review | 0
DRG-157 | Drawing 157 | Mechanical | A | 2025-01-11 |  | Approved | 0
DRG-158 | Drawing 158 | Architecture | B | 2025-04-07 | 2025-04-20 | Rejected | 0
DRG-159 | Drawing 159 | Architecture | B | 2025-02-10 | 2025-02-20 | Approved | 0
DRG-160 | Drawing 160 | Electrical | C | 2025-06-16 | 2025-06-21 | Pending | 102
DRG-161 | Drawing 161 | Architecture | A | 2025-07-16 | 2025-07-27 | Pending | 0
DRG-162 | Drawing 162 | Mechanical | B | 2025-09-10 | 2025-09-11 | Pending | 0
DRG-163 | Drawing 163 | Mechanical | D | 2025-01-02 | 2025-01-05 | Approved | 0
DRG-164 | Drawing 164 | Plumbing | B | 2025-07-08 |  | Pending | 0
DRG-165 | Drawing 165 | Plumbing | A | 2025-01-13 | 2025-01-25 | Pending | 239
DRG-166 | Drawing 166 | Civil | C | 2025-03-17 | 2025-03-17 | Rejected | 0
DRG-167 | Drawing 167 | Plumbing | B | 2025-08-12 | 2025-08-17 | For Review | 0
DRG-168 | Drawing 168 | Civil | A | 2025-05-24 | 2025-05-26 | For Review | 0
DRG-169 | Drawing 169 | Electrical | C | 2025-10-17 |  | Rejected | 0
DRG-170 | Drawing 170 | Plumbing | B | 2025-02-12 | 2025-02-27 | For Review | 0
DRG-171 | Drawing 171 | Architecture | C | 2025-02-04 | 2025-02-04 | Issued for Construction | 0
DRG-172 | Drawing 172 | Electrical | A | 2025-09-19 |  | Rejected | 0
DRG-173 | Drawing 173 | Architecture | C | 2025-07-24 | 2025-07-24 | Rejected | 0
DRG-174 | Drawing 174 | Mechanical | B | 2025-04-12 | 2025-04-25 | For Review | 0
DRG-175 | Drawing 175 | Mechanical | A | 2025-06-14 |  | Approved | 0
DRG-176 | Drawing 176 | Electrical | C | 2025-07-06 | 2025-07-19 | Rejected | 0
DRG-177 | Drawing 177 | Architecture | C | 2025-06-25 |  | Pending | 0
DRG-178 | Drawing 178 | Electrical | B | 2025-02-12 |  | Rejected | 0
DRG-179 | Drawing 179 | Architecture | D | 2025-09-22 | 2025-09-27 | For Review | 0
DRG-180 | Drawing 180 | Civil | C | 2025-09-21 |  | Approved | 0
DRG-181 | Drawing 181 | Mechanical | B | 2025-03-01 |  | For Review | 0
DRG-182 | Drawing 182 | Mechanical | A | 2025-06-24 | 2025-06-26 | For Review | 0
DRG-183 | Drawing 183 | Civil | C | 2025-10-19 |  | For Review | 0
DRG-184 | Drawing 184 | Mechanical | C | 2025-03-19 | 2025-04-03 | Approved | 0
DRG-185 | Drawing 185 | Architecture | A | 2025-07-10 | 2025-07-25 | Issued for Construction | 0
DRG-186 | Drawing 186 | Mechanical | C | 2025-09-09 | 2025-09-15 | Pending | 145
DRG-187 | Drawing 187 | Plumbing | B | 2025-07-21 | 2025-07-22 | For Review | 0
DRG-188 | Drawing 188 | Civil | B | 2025-05-12 | 2025-05-13 | Approved | 0
DRG-189 | Drawing 189 | Civil | C | 2025-04-17 |  | For Review | 0
DRG-190 | Drawing 190 | Plumbing | A | 2025-07-21 | 2025-08-02 | Approved | 0
DRG-191 | Drawing 191 | Civil | B | 2025-08-12 | 2025-08-15 | For Review | 0
DRG-192 | Drawing 192 | Electrical | C | 2025-02-24 |  | Approved | 0
DRG-193 | Drawing 193 | Electrical | B | 2025-08-26 | 2025-09-08 | For Review | 0
DRG-194 | Drawing 194 | Plumbing | C | 2025-08-05 | 2025-08-12 | Pending | 0
DRG-195 | Drawing 195 | Mechanical | C | 2025-01-04 | 2025-01-14 | Rejected | 0
DRG-196 | Drawing 196 | Architecture | B | 2025-08-28 | 2025-09-10 | Rejected | 0
DRG-197 | Drawing 197 | Civil | B | 2025-04-11 | 2025-04-24 | For Review | 0
DRG-198 | Drawing 198 | Plumbing | C | 2025-03-20 | 2025-04-01 | Issued for Construction | 0
DRG-199 | Drawing 199 | Electrical | B | 2025-09-13 | 2025-09-20 | Issued for Construction | 0
DRG-200 | Drawing 200 | Civil | A | 2025-06-21 | 2025-06-22 | Rejected | 0
DRG-201 | Drawing 201 | Plumbing | A | 2025-08-28 | 2025-09-09 | For Review | 0
DRG-202 | Drawing 202 | Plumbing | B | 2025-10-08 | 2025-10-18 | Issued for Construction | 0
DRG-203 | Drawing 203 | Mechanical | A | 2025-09-20 | 2025-09-22 | Rejected | 0
DRG-204 | Drawing 204 | Electrical | A | 2025-08-12 | 2025-08-13 | For Review | 0
DRG-205 | Drawing 205 | Civil | B | 2025-06-20 | 2025-06-25 | For Review | 0
DRG-206 | Drawing 206 | Civil | C | 2025-08-14 | 2025-08-27 | Rejected | 0
DRG-207 | Drawing 207 | Electrical | A | 2025-04-10 | 2025-04-22 | Rejected | 0
DRG-208 | Drawing 208 | Civil | A | 2025-06-10 | 2025-06-15 | Rejected | 0
DRG-209 | Drawing 209 | Mechanical | A | 2025-09-28 | 2025-10-02 | For Review | 0
DRG-210 | Drawing 210 | Plumbing | D | 2025-09-18 | 2025-09-29 | Issued for Construction | 0
DRG-211 | Drawing 211 | Architecture | C | 2025-08-25 | 2025-08-25 | For Review | 0
DRG-212 | Drawing 212 | Mechanical | C | 2025-08-25 |  | Issued for Construction | 0
DRG-213 | Drawing 213 | Civil | B | 2025-09-28 | 2025-10-05 | Approved | 0
DRG-214 | Drawing 214 | Architecture | D | 2025-04-17 | 2025-04-19 | Rejected | 0
DRG-215 | Drawing 215 | Electrical | A | 2025-09-25 | 2025-09-30 | Issued for Construction | 0
DRG-216 | Drawing 216 | Architecture | A | 2025-05-02 | 2025-05-04 | Pending | 0
DRG-217 | Drawing 217 | Architecture | A | 2025-10-20 |  | Issued for Construction | 0
DRG-218 | Drawing 218 | Mechanical | B | 2025-08-16 | 2025-08-24 | For Review | 0
DRG-219 | Drawing 219 | Electrical | D | 2025-05-28 | 2025-06-06 | Approved | 0
DRG-220 | Drawing 220 | Civil | B | 2025-01-28 |  | Pending | 165
DRG-221 | Drawing 221 | Plumbing | D | 2025-05-11 | 2025-05-20 | Issued for Construction | 0
DRG-222 | Drawing 222 | Architecture | C | 2025-02-11 | 2025-02-20 | Approved | 0
DRG-223 | Drawing 223 | Architecture | C | 2025-07-19 | 2025-07-28 | For Review | 0
DRG-224 | Drawing 224 | Architecture | D | 2025-01-10 |  | Issued for Construction | 0
DRG-225 | Drawing 225 | Civil | D | 2025-01-05 | 2025-01-06 | Issued for Construction | 0
DRG-226 | Drawing 226 | Plumbing | D | 2025-07-16 | 2025-07-31 | For Review | 0
DRG-227 | Drawing 227 | Electrical | C | 2025-05-27 |  | Pending | 0
DRG-228 | Drawing 228 | Civil | D | 2025-01-19 |  | Approved | 0
DRG-229 | Drawing 229 | Architecture | D | 2025-03-31 | 2025-04-14 | Approved | 0
DRG-230 | Drawing 230 | Plumbing | C | 2025-03-19 | 2025-03-23 | Pending | 0
DRG-231 | Drawing 231 | Civil | B | 2025-07-25 | 2025-07-27 | Pending | 125
DRG-232 | Drawing 232 | Architecture | C | 2025-08-15 | 2025-08-22 | Issued for Construction | 0
DRG-233 | Drawing 233 | Mechanical | A | 2025-05-02 | 2025-05-11 | Issued for Construction | 0
DRG-234 | Drawing 234 | Mechanical | B | 2025-10-14 | 2025-10-28 | Pending | 165
DRG-235 | Drawing 235 | Electrical | A | 2025-02-12 | 2025-02-21 | For Review | 0
DRG-236 | Drawing 236 | Civil | C | 2025-08-30 | 2025-08-31 | Rejected | 0
DRG-237 | Drawing 237 | Electrical | B | 2025-01-18 | 2025-01-27 | Pending | 0
DRG-238 | Drawing 238 | Mechanical | D | 2025-05-12 | 2025-05-19 | Rejected | 0
DRG-239 | Drawing 239 | Mechanical | C | 2025-02-23 |  | Approved | 0
DRG-240 | Drawing 240 | Architecture | C | 2025-04-15 | 2025-04-29 | For Review | 0
DRG-241 | Drawing 241 | Architecture | C | 2025-05-23 | 2025-05-31 | Approved | 0
DRG-242 | Drawing 242 | Architecture | B | 2025-02-26 |  | For Review | 0
DRG-243 | Drawing 243 | Mechanical | D | 2025-02-24 | 2025-02-25 | Issued for Construction | 0
DRG-244 | Drawing 244 | Electrical | A | 2025-06-05 |  | Approved | 0
DRG-245 | Drawing 245 | Plumbing | B | 2025-10-26 | 2025-10-30 | Pending | 177
DRG-246 | Drawing 246 | Civil | B | 2025-01-14 | 2025-01-25 | Issued for Construction | 0
DRG-247 | Drawing 247 | Mechanical | B | 2025-04-01 | 2025-04-07 | Pending | 84
DRG-248 | Drawing 248 | Civil | C | 2025-06-03 | 2025-06-15 | For Review | 0
DRG-249 | Drawing 249 | Electrical | D | 2025-09-14 | 2025-09-16 | Issued for Construction | 0
DRG-250 | Drawing 250 | Civil | D | 2025-07-15 |  | Approved | 0
DRG-251 | Drawing 251 | Civil | B | 2025-01-01 |  | Approved | 0
DRG-252 | Drawing 252 | Mechanical | B | 2025-06-04 |  | Approved | 0
DRG-253 | Drawing 253 | Civil | C | 2025-03-24 |  | Approved | 0
DRG-254 | Drawing 254 | Electrical | B | 2025-05-07 | 2025-05-14 | Approved | 0
DRG-255 | Drawing 255 | Plumbing | A | 2025-05-12 | 2025-05-12 | Pending | 221
DRG-256 | Drawing 256 | Plumbing | D | 2025-07-29 | 2025-07-31 | Pending | 209
DRG-257 | Drawing 257 | Civil | C | 2025-08-27 | 2025-09-02 | For Review | 0
DRG-258 | Drawing 258 | Electrical | B | 2025-08-27 |  | Pending | 232
DRG-259 | Drawing 259 | Plumbing | D | 2025-10-23 |  | For Review | 0
DRG-260 | Drawing 260 | Mechanical | A | 2025-09-20 | 2025-09-23 | Issued for Construction | 0
DRG-261 | Drawing 261 | Plumbing | B | 2025-06-24 | 2025-07-07 | Approved | 0
DRG-262 | Drawing 262 | Plumbing | A | 2025-06-18 | 2025-06-28 | Pending | 148
DRG-263 | Drawing 263 | Electrical | C | 2025-08-20 | 2025-08-23 | Issued for Construction | 0
DRG-264 | Drawing 264 | Electrical | D | 2025-07-17 | 2025-07-27 | Approved | 0
DRG-265 | Drawing 265 | Architecture | A | 2025-06-22 | 2025-06-22 | For Review | 0
DRG-266 | Drawing 266 | Mechanical | A | 2025-03-24 | 2025-04-06 | Pending | 0
DRG-267 | Drawing 267 | Civil | B | 2025-05-02 | 2025-05-13 | Pending | 54
DRG-268 | Drawing 268 | Mechanical | D | 2025-06-13 | 2025-06-21 | For Review | 0
DRG-269 | Drawing 269 | Electrical | A | 2025-05-13 | 2025-05-20 | Approved | 0
DRG-270 | Drawing 270 | Mechanical | A | 2025-02-07 | 2025-02-16 | Rejected | 0
DRG-271 | Drawing 271 | Civil | C | 2025-07-18 |  | For Review | 0
DRG-272 | Drawing 272 | Plumbing | D | 2025-02-05 | 2025-02-07 | Issued for Construction | 0
DRG-273 | Drawing 273 | Plumbing | B | 2025-04-25 | 2025-04-28 | Rejected | 0
DRG-274 | Drawing 274 | Electrical | A | 2025-05-30 | 2025-06-14 | Approved | 0
DRG-275 | Drawing 275 | Plumbing | A | 2025-02-04 |  | For Review | 0
DRG-276 | Drawing 276 | Electrical | B | 2025-07-12 | 2025-07-18 | For Review | 0
DRG-277 | Drawing 277 | Architecture | C | 2025-03-17 |  | For Review | 0
DRG-278 | Drawing 278 | Plumbing | B | 2025-07-07 | 2025-07-07 | Rejected | 0
DRG-279 | Drawing 279 | Electrical | D | 2025-03-26 |  | Issued for Construction | 0
DRG-280 | Drawing 280 | Plumbing | D | 2025-04-20 | 2025-04-20 | Issued for Construction | 0
DRG-281 | Drawing 281 | Mechanical | A | 2025-06-29 | 2025-07-12 | Approved | 0
DRG-282 | Drawing 282 | Plumbing | A | 2025-03-30 | 2025-03-30 | Rejected | 0
DRG-283 | Drawing 283 | Electrical | D | 2025-07-22 |  | Pending | 0
DRG-284 | Drawing 284 | Architecture | C | 2025-03-29 | 2025-04-06 | For Review | 0
DRG-285 | Drawing 285 | Electrical | C | 2025-10-25 | 2025-10-30 | Approved | 0
DRG-286 | Drawing 286 | Electrical | C | 2025-04-03 | 2025-04-10 | Rejected | 0
DRG-287 | Drawing 287 | Architecture | B | 2025-06-28 | 2025-06-30 | For Review | 0
DRG-288 | Drawing 288 | Plumbing | D | 2025-06-03 | 2025-06-17 | For Review | 0
DRG-289 | Drawing 289 | Mechanical | A | 2025-04-08 | 2025-04-13 | Pending | 0
DRG-290 | Drawing 290 | Mechanical | C | 2025-01-26 | 2025-02-02 | For Review | 0
DRG-291 | Drawing 291 | Electrical | D | 2025-05-29 | 2025-06-04 | Rejected | 0
DRG-292 | Drawing 292 | Plumbing | D | 2025-04-21 | 2025-04-25 | Approved | 0
DRG-293 | Drawing 293 | Architecture | B | 2025-10-23 | 2025-11-04 | Pending | 0
DRG-294 | Drawing 294 | Electrical | A | 2025-04-24 | 2025-05-07 | Rejected | 0
DRG-295 | Drawing 295 | Civil | D | 2025-01-29 | 2025-02-10 | Issued for Construction | 0
DRG-296 | Drawing 296 | Electrical | A | 2025-06-12 | 2025-06-13 | Approved | 0
DRG-297 | Drawing 297 | Architecture | A | 2025-04-06 | 2025-04-06 | Issued for Construction | 0
DRG-298 | Drawing 298 | Electrical | A | 2025-04-13 |  | Rejected | 0
DRG-299 | Drawing 299 | Architecture | C | 2025-09-02 | 2025-09-02 | Issued for Construction | 0
DRG-300 | Drawing 300 | Mechanical | A | 2025-08-03 | 2025-08-16 | Rejected | 0
DRG-301 | Drawing 301 | Architecture | D | 2025-06-03 | 2025-06-08 | Rejected | 0
DRG-302 | Drawing 302 | Plumbing | C | 2025-09-28 | 2025-10-11 | Issued for Construction | 0
DRG-303 | Drawing 303 | Electrical | B | 2025-01-29 | 2025-02-12 | Issued for Construction | 0
DRG-304 | Drawing 304 | Civil | A | 2025-08-05 | 2025-08-19 | Rejected | 0
DRG-305 | Drawing 305 | Electrical | B | 2025-07-25 | 2025-08-07 | Approved | 0
DRG-306 | Drawing 306 | Civil | A | 2025-09-28 | 2025-10-07 | Rejected | 0
DRG-307 | Drawing 307 | Electrical | B | 2025-01-22 |  | For Review | 0
DRG-308 | Drawing 308 | Electrical | D | 2025-08-20 | 2025-09-03 | Rejected | 0
DRG-309 | Drawing 309 | Civil | C | 2025-05-25 | 2025-06-06 | Pending | 142
DRG-310 | Drawing 310 | Architecture | B | 2025-04-24 | 2025-05-04 | Pending | 54
DRG-311 | Drawing 311 | Civil | A | 2025-01-24 | 2025-02-05 | Pending | 249
DRG-312 | Drawing 312 | Plumbing | B | 2025-07-07 | 2025-07-12 | For Review | 0
DRG-313 | Drawing 313 | Architecture | C | 2025-06-24 | 2025-07-05 | Approved | 0
DRG-314 | Drawing 314 | Civil | C | 2025-04-19 | 2025-04-21 | Pending | 0
DRG-315 | Drawing 315 | Civil | C | 2025-05-29 | 2025-06-01 | Approved | 0
DRG-316 | Drawing 316 | Plumbing | B | 2025-08-18 | 2025-08-29 | Pending | 0
DRG-317 | Drawing 317 | Mechanical | C | 2025-03-29 | 2025-04-13 | Rejected | 0
DRG-318 | Drawing 318 | Electrical | A | 2025-02-03 | 2025-02-06 | Approved | 0
DRG-319 | Drawing 319 | Electrical | D | 2025-08-21 | 2025-08-25 | Pending | 243
DRG-320 | Drawing 320 | Civil | D | 2025-08-22 | 2025-08-25 | For Review | 0
DRG-321 | Drawing 321 | Mechanical | D | 2025-02-03 | 2025-02-17 | Approved | 0
DRG-322 | Drawing 322 | Civil | D | 2025-01-20 |  | Issued for Construction | 0
DRG-323 | Drawing 323 | Mechanical | A | 2025-05-20 | 2025-06-02 | Approved | 0
DRG-324 | Drawing 324 | Plumbing | A | 2025-07-27 | 2025-08-11 | Issued for Construction | 0
DRG-325 | Drawing 325 | Architecture | C | 2025-04-26 | 2025-05-02 | Rejected | 0
DRG-326 | Drawing 326 | Architecture | A | 2025-04-06 | 2025-04-14 | Issued for Construction | 0
DRG-327 | Drawing 327 | Civil | C | 2025-02-20 | 2025-02-26 | Issued for Construction | 0
DRG-328 | Drawing 328 | Electrical | B | 2025-08-24 | 2025-08-25 | Rejected | 0
DRG-329 | Drawing 329 | Civil | D | 2025-08-14 | 2025-08-17 | Approved | 0
DRG-330 | Drawing 330 | Plumbing | D | 2025-01-12 | 2025-01-20 | Pending | 51
DRG-331 | Drawing 331 | Architecture | A | 2025-10-08 | 2025-10-10 | Pending | 0
DRG-332 | Drawing 332 | Electrical | A | 2025-06-13 | 2025-06-27 | Pending | 0
DRG-333 | Drawing 333 | Plumbing | D | 2025-09-15 | 2025-09-30 | Rejected | 0
DRG-334 | Drawing 334 | Electrical | C | 2025-10-02 |  | For Review | 0
DRG-335 | Drawing 335 | Civil | B | 2025-03-19 | 2025-03-22 | Rejected | 0
DRG-336 | Drawing 336 | Architecture | B | 2025-10-14 | 2025-10-27 | Pending | 226
DRG-337 | Drawing 337 | Electrical | C | 2025-04-26 | 2025-05-10 | Rejected | 0
DRG-338 | Drawing 338 | Plumbing | C | 2025-08-13 |  | Rejected | 0
DRG-339 | Drawing 339 | Architecture | A | 2025-05-12 | 2025-05-25 | Approved | 0
DRG-340 | Drawing 340 | Architecture | A | 2025-08-13 | 2025-08-25 | Pending | 170
DRG-341 | Drawing 341 | Plumbing | B | 2025-01-21 | 2025-01-24 | For Review | 0
DRG-342 | Drawing 342 | Plumbing | C | 2025-07-07 | 2025-07-21 | For Review | 0
DRG-343 | Drawing 343 | Civil | A | 2025-09-18 | 2025-09-19 | Issued for Construction | 0
DRG-344 | Drawing 344 | Plumbing | C | 2025-05-12 | 2025-05-16 | Rejected | 0
DRG-345 | Drawing 345 | Civil | D | 2025-06-18 | 2025-06-18 | Issued for Construction | 0
DRG-346 | Drawing 346 | Plumbing | B | 2025-01-30 | 2025-02-09 | Approved | 0
DRG-347 | Drawing 347 | Civil | B | 2025-02-19 | 2025-02-25 | Rejected | 0
DRG-348 | Drawing 348 | Architecture | C | 2025-08-08 | 2025-08-16 | Approved | 0
DRG-349 | Drawing 349 | Mechanical | D | 2025-06-06 | 2025-06-15 | Issued for Construction | 0
DRG-350 | Drawing 350 | Civil | A | 2025-06-15 | 2025-06-30 | Pending | 0
DRG-351 | Drawing 351 | Plumbing | B | 2025-02-28 | 2025-03-14 | For Review | 0
DRG-352 | Drawing 352 | Electrical | D | 2025-01-27 |  | For Review | 0
DRG-353 | Drawing 353 | Electrical | C | 2025-03-11 | 2025-03-12 | Pending | 95
DRG-354 | Drawing 354 | Architecture | A | 2025-02-04 |  | Rejected | 0
DRG-355 | Drawing 355 | Plumbing | A | 2025-07-10 | 2025-07-16 | Issued for Construction | 0
DRG-356 | Drawing 356 | Architecture | D | 2025-04-25 | 2025-05-04 | Issued for Construction | 0
DRG-357 | Drawing 357 | Architecture | D | 2025-10-27 | 2025-10-30 | Approved | 0
DRG-358 | Drawing 358 | Electrical | D | 2025-08-26 |  | Rejected | 0
DRG-359 | Drawing 359 | Civil | D | 2025-07-02 | 2025-07-03 | Pending | 252
DRG-360 | Drawing 360 | Plumbing | A | 2025-10-11 | 2025-10-24 | Approved | 0
DRG-361 | Drawing 361 | Civil | B | 2025-07-04 | 2025-07-18 | Rejected | 0
DRG-362 | Drawing 362 | Mechanical | A | 2025-01-31 | 2025-02-08 | Issued for Construction | 0
DRG-363 | Drawing 363 | Electrical | C | 2025-04-16 | 2025-04-30 | For Review | 0
DRG-364 | Drawing 364 | Architecture | B | 2025-02-26 | 2025-02-26 | Issued for Construction | 0
DRG-365 | Drawing 365 | Mechanical | B | 2025-08-29 | 2025-09-01 | Approved | 0
DRG-366 | Drawing 366 | Architecture | D | 2025-02-24 | 2025-03-03 | Approved | 0
DRG-367 | Drawing 367 | Plumbing | C | 2025-05-16 | 2025-05-28 | Rejected | 0
DRG-368 | Drawing 368 | Civil | A | 2025-04-03 | 2025-04-10 | For Review | 0
DRG-369 | Drawing 369 | Architecture | B | 2025-01-27 | 2025-01-27 | Pending | 0
DRG-370 | Drawing 370 | Plumbing | A | 2025-06-01 | 2025-06-04 | Issued for Construction | 0
DRG-371 | Drawing 371 | Plumbing | A | 2025-09-23 |  | Issued for Construction | 0
DRG-372 | Drawing 372 | Architecture | A | 2025-01-13 | 2025-01-13 | Pending | 178
DRG-373 | Drawing 373 | Architecture | B | 2025-09-20 | 2025-09-21 | Rejected | 0
DRG-374 | Drawing 374 | Plumbing | D | 2025-10-23 |  | Pending | 0
DRG-375 | Drawing 375 | Mechanical | D | 2025-06-19 | 2025-06-25 | For Review | 0
DRG-376 | Drawing 376 | Plumbing | D | 2025-09-23 | 2025-10-02 | Issued for Construction | 0
DRG-377 | Drawing 377 | Architecture | B | 2025-04-20 |  | Rejected | 0
DRG-378 | Drawing 378 | Plumbing | A | 2025-05-07 | 2025-05-22 | Pending | 0
DRG-379 | Drawing 379 | Civil | B | 2025-04-26 |  | Pending | 0
DRG-380 | Drawing 380 | Electrical | A | 2025-05-04 | 2025-05-08 | Pending | 187
DRG-381 | Drawing 381 | Architecture | D | 2025-10-08 | 2025-10-23 | Issued for Construction | 0
DRG-382 | Drawing 382 | Mechanical | D | 2025-04-26 | 2025-05-01 | For Review | 0
DRG-383 | Drawing 383 | Plumbing | B | 2025-02-11 |  | Rejected | 0
DRG-384 | Drawing 384 | Plumbing | C | 2025-04-15 | 2025-04-30 | Rejected | 0
DRG-385 | Drawing 385 | Plumbing | B | 2025-09-09 | 2025-09-12 | For Review | 0
DRG-386 | Drawing 386 | Mechanical | C | 2025-06-02 | 2025-06-17 | Approved | 0
DRG-387 | Drawing 387 | Electrical | C | 2025-01-09 | 2025-01-19 | Pending | 0
DRG-388 | Drawing 388 | Electrical | B | 2025-06-02 | 2025-06-15 | Issued for Construction | 0
DRG-389 | Drawing 389 | Architecture | D | 2025-04-15 | 2025-04-24 | Approved | 0
DRG-390 | Drawing 390 | Architecture | A | 2025-04-26 | 2025-05-02 | Issued for Construction | 0
DRG-391 | Drawing 391 | Civil | C | 2025-09-19 |  | Pending | 242
DRG-392 | Drawing 392 | Architecture | A | 2025-09-06 |  | For Review | 0
DRG-393 | Drawing 393 | Plumbing | C | 2025-04-11 | 2025-04-11 | Issued for Construction | 0
DRG-394 | Drawing 394 | Plumbing | A | 2025-09-19 | 2025-09-27 | Pending | 0
DRG-395 | Drawing 395 | Mechanical | B | 2025-04-01 | 2025-04-14 | Approved | 0
DRG-396 | Drawing 396 | Mechanical | C | 2025-09-06 | 2025-09-15 | Issued for Construction | 0
DRG-397 | Drawing 397 | Plumbing | D | 2025-04-21 | 2025-05-01 | Approved | 0
DRG-398 | Drawing 398 | Architecture | D | 2025-03-31 | 2025-04-09 | Issued for Construction | 0
DRG-399 | Drawing 399 | Electrical | A | 2025-07-01 | 2025-07-05 | Rejected | 0
DRG-400 | Drawing 400 | Civil | B | 2025-02-20 | 2025-02-23 | Rejected | 0
DRG-401 | Drawing 401 | Architecture | A | 2025-10-23 | 2025-10-29 | For Review | 0
DRG-402 | Drawing 402 | Architecture | B | 2025-01-07 | 2025-01-15 | Approved | 0
DRG-403 | Drawing 403 | Architecture | B | 2025-07-22 | 2025-07-23 | Approved | 0
DRG-404 | Drawing 404 | Mechanical | B | 2025-10-05 | 2025-10-14 | For Review | 0
DRG-405 | Drawing 405 | Plumbing | C | 2025-09-24 | 2025-10-07 | Rejected | 0
DRG-406 | Drawing 406 | Architecture | A | 2025-10-16 | 2025-10-27 | For Review | 0
DRG-407 | Drawing 407 | Plumbing | B | 2025-10-09 | 2025-10-18 | Issued for Construction | 0
DRG-408 | Drawing 408 | Mechanical | D | 2025-06-04 | 2025-06-05 | Issued for Construction | 0
DRG-409 | Drawing 409 | Architecture | D | 2025-01-09 | 2025-01-15 | Pending | 130
DRG-410 | Drawing 410 | Civil | B | 2025-07-16 | 2025-07-25 | For Review | 0
DRG-411 | Drawing 411 | Electrical | C | 2025-03-22 | 2025-03-28 | Approved | 0
DRG-412 | Drawing 412 | Mechanical | D | 2025-01-12 | 2025-01-25 | Rejected | 0
DRG-413 | Drawing 413 | Architecture | C | 2025-07-15 | 2025-07-19 | Pending | 0
DRG-414 | Drawing 414 | Plumbing | B | 2025-09-22 | 2025-09-29 | Approved | 0
DRG-415 | Drawing 415 | Architecture | C | 2025-05-22 |  | Pending | 67
DRG-416 | Drawing 416 | Plumbing | C | 2025-04-14 | 2025-04-19 | Pending | 275
DRG-417 | Drawing 417 | Electrical | C | 2025-06-01 |  | Issued for Construction | 0
DRG-418 | Drawing 418 | Mechanical | C | 2025-08-04 | 2025-08-05 | Pending | 208
DRG-419 | Drawing 419 | Mechanical | C | 2025-06-01 | 2025-06-12 | Pending | 270
DRG-420 | Drawing 420 | Architecture | B | 2025-06-28 |  | Approved | 0
DRG-421 | Drawing 421 | Civil | C | 2025-09-29 | 2025-10-12 | Approved | 0
DRG-422 | Drawing 422 | Architecture | A | 2025-09-06 | 2025-09-12 | Pending | 0
DRG-423 | Drawing 423 | Civil | C | 2025-09-16 | 2025-09-25 | Approved | 0
DRG-424 | Drawing 424 | Mechanical | C | 2025-04-21 | 2025-04-24 | Issued for Construction | 0
DRG-425 | Drawing 425 | Architecture | A | 2025-08-31 | 2025-09-12 | Rejected | 0
DRG-426 | Drawing 426 | Mechanical | D | 2025-05-16 | 2025-05-23 | Pending | 239
DRG-427 | Drawing 427 | Mechanical | B | 2025-02-06 | 2025-02-18 | Issued for Construction | 0
DRG-428 | Drawing 428 | Electrical | A | 2025-05-26 | 2025-06-02 | Issued for Construction | 0
DRG-429 | Drawing 429 | Civil | D | 2025-02-13 | 2025-02-27 | For Review | 0
DRG-430 | Drawing 430 | Civil | A | 2025-06-18 | 2025-06-19 | Issued for Construction | 0
DRG-431 | Drawing 431 | Mechanical | A | 2025-09-08 | 2025-09-18 | Rejected | 0
DRG-432 | Drawing 432 | Civil | A | 2025-05-17 |  | For Review | 0
DRG-433 | Drawing 433 | Electrical | A | 2025-10-28 | 2025-10-29 | Pending | 281
DRG-434 | Drawing 434 | Mechanical | B | 2025-01-16 | 2025-01-17 | For Review | 0
DRG-435 | Drawing 435 | Civil | C | 2025-02-02 | 2025-02-13 | For Review | 0
DRG-436 | Drawing 436 | Civil | A | 2025-09-22 | 2025-09-24 | Approved | 0
DRG-437 | Drawing 437 | Electrical | C | 2025-09-26 |  | For Review | 0
DRG-438 | Drawing 438 | Architecture | C | 2025-09-05 | 2025-09-15 | Rejected | 0
DRG-439 | Drawing 439 | Civil | C | 2025-08-21 | 2025-08-23 | For Review | 0
DRG-440 | Drawing 440 | Electrical | D | 2025-04-23 | 2025-04-28 | Rejected | 0
DRG-441 | Drawing 441 | Civil | A | 2025-07-15 | 2025-07-20 | For Review | 0
DRG-442 | Drawing 442 | Civil | B | 2025-07-26 | 2025-07-27 | Approved | 0
DRG-443 | Drawing 443 | Plumbing | A | 2025-07-01 | 2025-07-15 | Pending | 0
DRG-444 | Drawing 444 | Plumbing | A | 2025-01-25 | 2025-02-04 | Pending | 229
DRG-445 | Drawing 445 | Civil | C | 2025-08-02 |  | Approved | 0
DRG-446 | Drawing 446 | Electrical | D | 2025-08-03 | 2025-08-12 | For Review | 0
DRG-447 | Drawing 447 | Plumbing | C | 2025-01-09 | 2025-01-18 | Approved | 0
DRG-448 | Drawing 448 | Civil | C | 2025-06-19 | 2025-06-21 | For Review | 0
DRG-449 | Drawing 449 | Civil | C | 2025-10-01 |  | Approved | 0
DRG-450 | Drawing 450 | Architecture | A | 2025-06-09 | 2025-06-23 | Issued for Construction | 0
DRG-451 | Drawing 451 | Civil | C | 2025-01-09 | 2025-01-17 | For Review | 0
DRG-452 | Drawing 452 | Civil | C | 2025-06-16 | 2025-06-28 | Rejected | 0
DRG-453 | Drawing 453 | Civil | D | 2025-05-17 | 2025-05-28 | Approved | 0
DRG-454 | Drawing 454 | Civil | D | 2025-10-03 |  | Issued for Construction | 0
DRG-455 | Drawing 455 | Plumbing | B | 2025-10-19 | 2025-10-20 | Rejected | 0
DRG-456 | Drawing 456 | Plumbing | C | 2025-09-20 | 2025-09-20 | Issued for Construction | 0
DRG-457 | Drawing 457 | Civil | A | 2025-07-26 | 2025-08-03 | Pending | 93
DRG-458 | Drawing 458 | Mechanical | A | 2025-10-19 | 2025-10-26 | Pending | 0
DRG-459 | Drawing 459 | Architecture | B | 2025-01-15 | 2025-01-22 | Pending | 132
DRG-460 | Drawing 460 | Plumbing | D | 2025-10-13 | 2025-10-17 | Approved | 0
DRG-461 | Drawing 461 | Plumbing | D | 2025-04-02 | 2025-04-10 | For Review | 0
DRG-462 | Drawing 462 | Plumbing | C | 2025-06-21 |  | Pending | 0
DRG-463 | Drawing 463 | Architecture | D | 2025-08-30 | 2025-08-30 | Rejected | 0
DRG-464 | Drawing 464 | Architecture | C | 2025-05-09 | 2025-05-13 | For Review | 0
DRG-465 | Drawing 465 | Architecture | B | 2025-06-13 | 2025-06-14 | Rejected | 0
DRG-466 | Drawing 466 | Plumbing | B | 2025-10-23 | 2025-11-02 | Issued for Construction | 0
DRG-467 | Drawing 467 | Mechanical | B | 2025-07-28 |  | Pending | 60
DRG-468 | Drawing 468 | Mechanical | D | 2025-02-07 | 2025-02-17 | Rejected | 0
DRG-469 | Drawing 469 | Electrical | D | 2025-05-13 | 2025-05-16 | Rejected | 0
DRG-470 | Drawing 470 | Electrical | C | 2025-03-12 | 2025-03-15 | For Review | 0
DRG-471 | Drawing 471 | Civil | A | 2025-04-10 | 2025-04-10 | Pending | 0
DRG-472 | Drawing 472 | Civil | C | 2025-09-29 | 2025-10-06 | Rejected | 0
DRG-473 | Drawing 473 | Civil | C | 2025-02-07 | 2025-02-20 | Approved | 0
DRG-474 | Drawing 474 | Civil | C | 2025-05-14 | 2025-05-16 | Approved | 0
DRG-475 | Drawing 475 | Plumbing | D | 2025-08-10 | 2025-08-18 | Rejected | 0
DRG-476 | Drawing 476 | Plumbing | A | 2025-02-02 | 2025-02-13 | Approved | 0
DRG-477 | Drawing 477 | Architecture | A | 2025-03-13 |  | Rejected | 0
DRG-478 | Drawing 478 | Civil | A | 2025-04-28 | 2025-05-11 | Rejected | 0
DRG-479 | Drawing 479 | Electrical | D | 2025-07-10 | 2025-07-17 | Pending | 0
DRG-480 | Drawing 480 | Plumbing | D | 2025-05-22 | 2025-05-31 | For Review | 0
DRG-481 | Drawing 481 | Plumbing | C | 2025-05-11 |  | For Review | 0
DRG-482 | Drawing 482 | Architecture | C | 2025-05-08 | 2025-05-16 | Pending | 226
DRG-483 | Drawing 483 | Mechanical | A | 2025-07-05 | 2025-07-05 | Rejected | 0
DRG-484 | Drawing 484 | Architecture | C | 2025-03-16 | 2025-03-28 | Rejected | 0
DRG-485 | Drawing 485 | Civil | C | 2025-10-27 | 2025-10-28 | Issued for Construction | 0
DRG-486 | Drawing 486 | Mechanical | B | 2025-07-12 | 2025-07-26 | Pending | 0
DRG-487 | Drawing 487 | Architecture | A | 2025-08-26 |  | Rejected | 0
DRG-488 | Drawing 488 | Plumbing | B | 2025-05-20 | 2025-05-22 | Issued for Construction | 0
DRG-489 | Drawing 489 | Mechanical | C | 2025-07-18 | 2025-07-31 | Issued for Construction | 0
DRG-490 | Drawing 490 | Electrical | C | 2025-04-10 |  | Rejected | 0
DRG-491 | Drawing 491 | Mechanical | B | 2025-10-18 | 2025-10-25 | Approved | 0
DRG-492 | Drawing 492 | Civil | B | 2025-05-03 | 2025-05-17 | Rejected | 0
DRG-493 | Drawing 493 | Civil | D | 2025-08-25 |  | Issued for Construction | 0
DRG-494 | Drawing 494 | Architecture | B | 2025-03-04 | 2025-03-15 | Approved | 0
DRG-495 | Drawing 495 | Mechanical | D | 2025-10-27 | 2025-11-11 | Rejected | 0
DRG-496 | Drawing 496 | Plumbing | D | 2025-07-01 |  | Approved | 0
DRG-497 | Drawing 497 | Civil | A | 2025-01-13 | 2025-01-28 | Issued for Construction | 0
DRG-498 | Drawing 498 | Electrical | C | 2025-01-26 |  | Issued for Construction | 0
DRG-499 | Drawing 499 | Electrical | D | 2025-10-23 | 2025-11-02 | Issued for Construction | 0
DRG-500 | Drawing 500 | Architecture | C | 2025-10-14 | 2025-10-24 | Issued for Construction | 0